## 📊 Executive Summary
QA EXECUTION REPORT
Sanctuary Nature Foundation – Donate Module ¦ Automated UI / Functional / Boundary Validation
Project Name |  |  | Sanctuary Nature Foundation – Donate Module
Test Execution Date |  |  | 2026-02-24
Testing Type |  |  | Automated UI / Functional / Boundary Validation
Framework / Environment |  |  | Pytest 8.2.0 ¦ Windows 11 ¦ Python 3.14.0
Report Prepared By |  |  | QA Engineering Team
Report Version |  |  | v1.0 – Production Release
Total Test Cases |  | Tests Passed |  | Tests Failed
74 |  | 68 |  | 6
Pass Rate |  | Defects Logged |  | Critical/High
91.8% |  | 6 |  | 3
TEST EXECUTION SUMMARY BY MODULE
TC ID | Module | Test Scenario | Total Sub-Tests | Passed | Failed | Pass Rate | Status
TC-001 | UI State | Verify Page Load and Default UI | 5 | 5 | 0 | 100% | PASS
TC-002 | Happy Path | Verify valid submissions | 8 | 8 | 0 | 100% | PASS
TC-003 | Dropdown | Verify Inspiration Dropdown | 7 | 7 | 0 | 100% | PASS
TC-004 | Validation | Verify Mandatory Fields | 5 | 5 | 0 | 100% | PASS
TC-005 | Security | Verify Name & Address XSS/SQLi | 6 | 6 | 0 | 100% | PASS
TC-006 | Boundary | Verify Max Length Bounds | 4 | 4 | 0 | 100% | PASS
TC-007 | Validation | Verify PAN Format Rules | 9 | 8 | 1 | 88.9% | FAIL
TC-008 | Validation | Verify Email Format Rules | 6 | 5 | 1 | 83.3% | FAIL
TC-009 | Validation | Verify Mobile Format Rules | 6 | 3 | 3 | 50.0% | FAIL
TC-010 | Amount | Verify Custom Amount Selection | 18 | 17 | 1 | 94.4% | FAIL
TOTAL | — | — | 74 | 68 | 6 | 0.91892 | —
KEY FINDINGS & RISKS
⚠ High reliance on 'novalidate' form attribute without adequate custom JS validation fallback.
⚠ Missing front-end data sanitization on Mobile and Email fields.
⚠ Custom amount field lacks numerical boundaries, risking payment gateway failure.
RECOMMENDATION
🚫 DO NOT push to production until the 6 identified validation defects are patched in the front-end JavaScript. All 4 failing test cases (TC-007, TC-008, TC-009, TC-010) must reach 100% pass rate before release sign-off.

## 🧪 Test Cases
TEST CASE REGISTER — DONATE MODULE
Module: Donate Module ¦ Framework: Pytest 8.2.0 ¦ Date: 2026-02-24 ¦ Total TCs: 10
TC ID | Module | Test Scenario | Test Type | Total Sub-Tests | Passed | Failed | Pass % | Overall Status | Priority | Remarks
TC-001 | UI State | Verify Page Load and Default UI | UI/Smoke | 5 | 5 | 0 | 0% | PASS | High | All UI elements render correctly
TC-002 | Happy Path | Verify valid donation submissions | Functional | 8 | 8 | 0 | 0% | PASS | Critical | End-to-end happy path validated
TC-003 | Dropdown | Verify Inspiration Dropdown behaviour | Functional | 7 | 7 | 0 | 0% | PASS | Medium | All dropdown options verified
TC-004 | Validation | Verify Mandatory Fields enforcement | Validation | 5 | 5 | 0 | 0% | PASS | High | Required field validations working
TC-005 | Security | Verify Name & Address XSS/SQLi resistance | Security | 6 | 6 | 0 | 0% | PASS | Critical | No injection vulnerability found
TC-006 | Boundary | Verify Max Length field boundaries | Boundary | 4 | 4 | 0 | 0% | PASS | Medium | Max-length constraints respected
TC-007 | Validation | Verify PAN format rules | Validation | 9 | 8 | 1 | 12.5% | FAIL | High | Lowercase PAN not rejected (DEF-004)
TC-008 | Validation | Verify Email format rules | Validation | 6 | 5 | 1 | 20% | FAIL | High | Missing TLD not caught (DEF-005)
TC-009 | Validation | Verify Mobile number format rules | Validation | 6 | 3 | 3 | 100% | FAIL | Critical | 3 mobile formats accepted incorrectly
TC-010 | Amount | Verify Custom Amount selection & bounds | Boundary | 18 | 17 | 1 | 5.882% | FAIL | Critical | Overflow amount not blocked (DEF-006)
TOTAL | — | — | — | 74 | 68 | 6 | 91.89% | — | — | —

## 🐛 Defect Log
DEFECT LOG — DONATE MODULE
Total Defects: 6 ¦ High/Critical: 3 ¦ Medium: 3 ¦ Status: All Open – Awaiting Fix
Defect ID | Associated TC | Module | Bug Description | Steps to Reproduce | Expected Result | Actual Result (Pytest Output) | Severity | Status | Owner
DEF-001 | TC-009 | Mobile Validation | Mobile field accepts extra formatting characters | 1. Enter +91-98765-43210-extra 2. Click Proceed | JS validation blocks input and shows error. | BUG: No error shown for invalid mobile '+91-98765-43210-extra' | Medium | Open | Front-End Dev
DEF-002 | TC-009 | Mobile Validation | Mobile field accepts strings under 10 digits | 1. Enter 12345 2. Click Proceed | JS validation blocks short digit strings. | BUG: No error shown for invalid mobile '12345' | Medium | Open | Front-End Dev
DEF-003 | TC-009 | Mobile Validation | Mobile field accepts alphabetic strings | 1. Enter abcdefghij 2. Click Proceed | JS validation blocks non-numeric characters. | BUG: No error shown for invalid mobile 'abcdefghij' | High | Open | Front-End Dev
DEF-004 | TC-007 | PAN Validation | PAN field does not enforce uppercase validation | 1. Enter lowercase PAN abcps1234d 2. Click Proceed | Form displays error or transforms to uppercase on submit. | BUG [Lowercase]: No error shown for invalid PAN 'abcps1234d' | Medium | Open | Front-End Dev
DEF-005 | TC-008 | Email Validation | Email field accepts strings without Top Level Domains | 1. Enter missing@domain into Email field 2. Click Proceed | novalidate requires JS to catch missing TLDs; form blocks submission. | BUG: No error shown for invalid email 'missing@domain' | High | Open | Front-End Dev
DEF-006 | TC-010 | Amount Validation | Custom amount field lacks character boundary / integer overflow limit | 1. Click 'Other' amount tab 2. Enter 999999999999999999 3. Click Proceed | JS validates and blocks integer overflow amounts. | BUG: No validation error shown for invalid amount '99999999999999999999' | High | Open | Front-End Dev

## 📈 Dashboard
QA DASHBOARD — LIVE METRICS
|  |  |  | Metric | Count
|  |  |  | Passed | 68
Total Test Cases | Total Sub-Tests | Passed Sub-Tests | Failed Sub-Tests
74 | 74 | 68 | 6
|  |  |  | High | 3
Overall Pass Rate | Total Defects | High Severity | Medium Severity
91.8% | 6 | 3 | 3
Defect Density | Release Decision | Retest Required | Sign-off Status
8.1% | BLOCK | YES | PENDING

## ✅ Release Checklist
PRODUCTION RELEASE QA GATE CHECKLIST
Release Gate Status: ❌ BLOCKED — Resolve all FAIL items before go-live
# | Gate Criterion | Owner | Target Date | Status | Notes
1 | All Test Cases executed with documented results | QA Lead | 2026-02-25 | ✅ PASS | 10/10 TCs executed
2 | All PASS test cases re-verified | QA Lead | 2026-02-25 | ✅ PASS | TC-001 to TC-006 pass 100%
3 | Defect DEF-003 (Mobile Alpha) — High patched & retested | Dev + QA | 2026-02-26 | ❌ OPEN | Awaiting front-end fix
4 | Defect DEF-005 (Email TLD) — High patched & retested | Dev + QA | 2026-02-26 | ❌ OPEN | JS regex update required
5 | Defect DEF-006 (Amount Overflow) — High patched & retested | Dev + QA | 2026-02-26 | ❌ OPEN | Max-length / boundary check missing
6 | Defect DEF-001 (Mobile Extra Chars) — Medium patched | Dev + QA | 2026-02-27 | ❌ OPEN | Awaiting front-end fix
7 | Defect DEF-002 (Mobile Short) — Medium patched | Dev + QA | 2026-02-27 | ❌ OPEN | Awaiting front-end fix
8 | Defect DEF-004 (PAN Lowercase) — Medium patched | Dev + QA | 2026-02-27 | ❌ OPEN | Regex uppercase enforcement needed
9 | Regression test suite executed after all patches | QA Lead | 2026-02-28 | ⏳ PENDING | Blocked by open defects
10 | Security review sign-off (XSS/SQLi) | Security | 2026-02-25 | ✅ PASS | TC-005 full pass
11 | Stakeholder QA sign-off received | PM / QA Lead | TBD | ⏳ PENDING | Awaiting defect resolution
12 | Production deployment approval | Release Mgr | TBD | ❌ BLOCKED | Cannot approve with open High defects